## Sp inputs
High level ideas / Features
Create Account
View Restaurants
Search Restaurants
View Menu
Add to Cart
Purchase
Restaurant views order
Restaurant marks order as delivered
Notes:
The above points were listed as draft ideas by the project sponsor.
The project sponsor mentioned that he wants to compete against Talabat.
As a sponsor, I am planning to compete against Talabat.
This is a view only file, you can make a copy then edit in the copy.
You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Backlog
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
Create an account | As a user I want to create a account for the me by {username - Email address - Phone num}, set password complexity, set location info , to being able to use the app with the most friendly UI | High | TRUE | 1 | To be started
View / search resturants | As a user I want to check the available restaurants, the best offers, sorted down by { Nearest, best offers, rapid delivery, customers previous feedback } so that I can order the most suitable meal. | High | TRUE | 1 | To be started
View menu | As a user I want to view the resturant menu items and each item details such as price, ingredients so that I can pick my favourite items. | High | TRUE | 1 | To be started
Add to cart | As a user I want to be able to add items to my shopping cart so that I can place the order | High | TRUE | 2 | To be started
Purchase | As a user I want to be able to add a payment card so that I can pay online. | High | TRUE | 2 | To be started
Restaurant views order | As a resturant I want to able to view orders so that I choose to accept it or not. | High | TRUE | 3 | To be started
Restaurant marks order as delivered | As a resturant I want to able to mark orders as delivered so that the user can review the order. | High | TRUE | 3 | To be started

## Sheet1
Time |  | Task
Day | Dates | Planning | Actual
OCT | Week 1 | 1 | 1
OCT | Week 2 | 1 | 1
OCT | Week 3 | 2 | 2
OCT | Week 4 | 3 | 2
Nov | Week 5 | 5 | 3
Nov | Week 6 | 6 | 5
Nov | Week 7 | 6 | 6
Nov | Week 8 | 7 | 7
Dec | Week 9 | 8 | 7
Dec | Week 10 | 10 | 9
Dec | Week 11 | 11 | 9
Dec | Week 12 | 11 | 11
Jan | Week 13 | 11 | 11
Jan | Week 14 | 13 | 13
Jan | Week 15 | 14 | 13
Jan | Week 16 | 15 | 14
FEB | Week 17 | 15 | 15